## Instructions
Instructions
You will use a Gantt chart to track the main phases of the client website project. This Gantt chart has already been filled out as an example. Download the template to add your own information.
The first row shows the start and end date for the entire project. In this example, the project starts on August 24 and ends on December 15. It also shows the number of total days estimated to complete the entire project. For your project, change the start and end dates to match the date when you started working on Unit 3 and when you think you will complete the course.
Look at row two. The first phase of the project is projected to start on 8/24 and end on 9/4. That means that it is estimated that it will take 12 days to complete phase 1. In the example below, phase 1 is complete , so the project manager has entered the actual number of days it took to complete phase 1, which is 8 days. The project manager allowed 12 days for that phase, but it was finished in only 8 days.
WBS (Work Breakdown Structure) The first column assigns numbers for each task according to its phase and order of performance within the phase.
Status
The second column tracks the status of each task. Currently, all of the cells are showing complete. Depending on the status, you may type in complete, late, at risk, or on schedule.
Start and End Dates
To adjust the start and end dates for each task, click inside the cell, change the date, and press Enter. The number of work days should update automatically. If it does not update automatically, you may have to use a calendar to determine the number of days.
Percent Complete
The completion percentage is currently set to 100 percent. When you update a status to complete, update the % complete column to 100 percent.

## Example Gantt Chart
Project Management Gantt Chart: Website Development
WBS | Status | Task | Start | End | Estimated # of Days | Actual Number of Days | % Complete | Notes
|  | Design Client Website | 2016-08-24 | 2016-12-15 | 82 | 66 | 100%
1 | Complete | Phase 1: Initiating the Project | 2016-08-24 | 2016-09-04 | 8 | 8 | 100%
1.1 | Complete | Locate a nonprofit client | 2016-08-24 | 2016-08-26 | 3 | 2 | 100%
1.2 | Complete | Complete Client Questionnaire/Needs Assessment Interview | 2016-09-01 | 2016-09-04 | 2 | 2 | 100% | Phase 1 is complete
2 |  | Phase 2: Planning Phase | 2016-09-05 | 2016-09-08 | 4 | 2 | 100%
2.1 | Complete | Complete an Audience Analysis | 2016-09-05 | 2016-09-08 | 4 | 2 | 100% | Phase 2 is complete
3 | Complete | Phase 3: Design Phase | 2016-09-09 | 2016-09-24 | 11 | 14 | 100%
3.1 | Complete | Complete Website Design and Navigation Worksheet | 2016-10-02 | 2016-10-05 | 3 | 3 | 100%
3.2 | Complete | Complete Website Design and Navigational Structure Peer Review Discussion | 2016-10-07 | 2016-10-08 | 1 | 2 | 100%
3.3 | Complete | Complete Website Design and Evaluation Paper | 2016-09-19 | 2016-09-19 |  | 4 | 100%
3.4 | Complete | Complete Accessibility Paper | 2016-09-20 | 2016-09-22 | 3 | 3 | 100%
3.5 | Complete | Complete Website Marketing Activity | 2016-09-23 | 2016-09-24 | 1 | 2 | 100% | Phase 3 is complete
4 | Complete | Phase 4: Development Phase | 2016-09-25 | 2016-10-28 | 25 | 25 | 100%
4.1 | Complete | Create four HTML web pages | 2016-09-26 | 2016-10-01 | 5 | 4 | 100%
4.2 | Complete | Create a Cascading Style Sheet | 2016-10-01 | 2016-10-03 | 1 | 2 | 100%
4.3 | Complete | Create an HTML web page with JavaScript to redirect visitors | 2016-10-03 | 2016-10-05 | 3 | 1 | 100%
4.4 | Complete | Create an HTML web page with JavaScript to add date and time | 2016-10-05 | 2016-10-07 | 3 | 2 | 100%
4.5 | Complete | Create an HTML web page with a JavaScript rollover image | 2016-10-07 | 2016-10-09 | 1 | 1 | 100%
4.6 | Complete | Compile a Java applet | 2016-10-09 | 2016-10-13 | 4 | 1 | 100%
4.7 | Complete | JavaScript Discussion and Peer Review | 2016-10-13 | 2016-10-16 | 2 | 2 | 100%
4.8 | Complete | Project Management Update with Teacher 1 | 2016-10-16 | 2016-10-18 | 2 | 1 | 100%
4.9 | Complete | Create HTML web page with an image | 2016-10-18 | 2016-10-20 | 3 | 2 | 100%
4.9.1 | Complete | Create a video | 2016-10-20 | 2016-10-25 | 4 | 4 | 100%
4.9.2 | Complete | Create web-based animation | 2016-10-25 | 2016-10-28 | 4 | 3 | 100%
4.9.3 | Complete | Project Management Update with Teacher 2 | 2016-11-14 | 2016-11-16 | 3 | 2 | 100% | Phase 4 is complete
4.9.4 | Complete | Phase 5: Launching the Site | 2016-11-17 | 2016-12-15 | 21 | 18 | 100%
4.9.5 | Complete | Complete Final Technical Report | 2016-11-25 | 2016-12-01 | 5 | 4 | 100%
4.9.6 | Complete | Complete Website Portfolio | 2016-12-02 | 2016-12-15 | 10 | 8 | 100% | All phases are complete
Formulas:
Estimated # of Days = IF([WBS]="Complete","",IF([End]-[Start]=0,"",NETWORKDAYS([Start],[End])))